## Worksheet
No | ID Meeting Level 1 | Point Of Meeting | PIC | DUE | STATUS
1 | 9 | Closing cost RM harus diangka 1 M | Plant & SM | 2023-07-01 | OPEN
2 | 9 | Tarik unit EX209 landclearing dari MME | Plant & SM | 2023-07-01 | OPEN
3 | 9 | Schedulling backlog dan menunggu penyesuaian jadwal BL J | Plant & SM | 2023-07-01 | OPEN
4 | 9 | Waiting schedulling repair coupling radial swing BL K | Plant & SM | 2023-07-01 | OPEN
5 | 9 | Penambahan high risk di setiap activity plan | Plant & SM | 2023-07-01 | OPEN
6 | 9 | Permintaan report bulanan harga fuel industri, harga backcharge subcont | Plant & SM | 2023-07-01 | OPEN